## Sheet2
Resilience Toolkit Action Plan
Whole School Approach Principle | Actions (what are you planning to achieve) | What will this achieve? How will you measure the impact? | Who is responsible for the action | To be completed by | What resources are needed | What other plans does this action link to | Status of action | Date action achieved | Comments | Review
3. Enabling student voice to influence decisions | To carry out student wellbeing surveys for years 7 and 9 so we have a baseline data at the start of the programme. | The feedback will help us devise a action plan which will address issues highlighted by the students. | Named staff member/team | May 2017 | Computer rooms, staffing, change of timetable, Instruction sheets | SIP | Surveys completed on time | 2017-05-01 | Completion within timeframe in a large school is challenging. Results received and presented to the extended leadership team. Headline results on December newsletter for staff, parents and students. Also to be included in assembly Jan 2018 | N/A See survey for 2017/2018.
1. Leadership and management that supports and champions efforts to promote emotional health and wellbeing | To appoint a member of staff to co-ordinate all aspects of student wellbeing across the school. | A point of contact for all agencies and staff to communicate with to ensure the smooth and effective implimentation of the Headstart programme and othe inititives. The results of the student, staff and parents surveys. | Named staff member/team | September 2017 | Mobile devise, job description, staff time | SIP | Appointment made to be reviewed after one year |  | Coordinator appointed as Student wellbeing coordinator started in Septemeber 2017 on one year contact to be reviewed at the end of the academic year. | Position to be approved to continue 2018 onwards. Mobile devise needed before GDPR.
1. Leadership and management that supports and champions efforts to promote emotional health and wellbeing | To build a Headstart team where each member represents and is responsible for a specific area of the tool kit/ action plan requirements. | It will ensure a whole school approach is achieved and that the team's experience and knowledge helps to put actions in place. Will enable programme to be sustainable over time. | Named staff member/team | September 2017 | Meeting room. Headstart packs - copies of workbook | SIP | Team in place and meeting termly |  | HeadStart team includes: Lead, Co-ordinator, Training, Safeguarding, Student leadership, PSHRE, SEN, Transition. Team meet every term to review progress and approve initiatives. | Lack of attendance to meeting due to teaching commitments and changes - review time and day of meeting termly.
3. Enabling student voice to influence decisions | To design and carry out an online survey specific to well-being at School. To share survey results with students. | To measure understanding of wellbeing and levels of wellbeing to provide baseline data. Impact measured by re-surveying on an annual basis. Survey specific to our school. | Named staff member/team | December 2017 | Staff time to develop and evaluate survey and time from PSHRE programme to conduct survey. | SIP | Internal survey in draft format |  | Surveys have been approved and sent out. Staff and Parents responses have been analised and sent to the appropriate staff to action. The student surveys are being carried out at the moment. | Staff survey been actioned by SLT. Student and Parent surveys yet to be actioned.
4. Staff development to support their own wellbeing and that of students | To organise staff training - Domains, YMHFA and Mindfulness | A whole school approach will be achieved and increase the understanding of the link between emotional wellbeing and attainment. Impact measured via survey results (external and internal), attendance and attainment data. | Named staff member/team | 2018-02-01 | Access to Hub and staff training time. | SIP | Dates planned for whole staff sessions. |  | Whole staff sessions are booked and planned. Further sessions are proving difficult to book due to lack of dates available from training providers. Dates for level 2 Mindfulness have now been agreed and three staff have been allocated spaces. YMHFA training have also given dates and four members of pastoral staff have been allocated spaces. | All training came at the same time which caused backlog of workload and impacted on teams. Teaching staff not receiving training due to costs involved. Need to schedule mental health training feedback on staff training days/slots
1. Leadership and management that supports and champions efforts to promote emotional health and wellbeing | To add wellbeing items to college and senior team meeting agendas. | All areas of the school will be updated on whole school progress and have an opportunity to put forward further ideas for implementation. As such, systems will become embedded into the school ethos. Recorded via meeting minutes. | Named staff member/team | November 2017 | Time element. | SIP | Not yet introduced |  | Coordinator was present at student team meeting to discuss resilience conversations, also discussed at FLO meetings. Staff team meeting have discussed staff survey. | Coordinator to join Student team. Other members of Headstart team to represent Wellbeing at other hard delivery teams.
2. Curriculum, teaching and learning to promote resilience and support social and emotional learning | To ensure that resilience and wellbeing is included in the PSHRE and assembly programmes (term 3 introduction). | Students will have opportunities to learn more about wellbeing, mindfulness, mindset and resilience. Impact measured by participation in interventions. | Named staff member/team | January 2018 | Resources created for session delivery. Printing costs and development time. | SIP | In PSHRE Programme for Term 3 |  | Lessons planned for term three for all year groups. 6th form have an outside agency coming intoo school to run wellbeing sessions. | Cordinator to meet at a regular specific time termly with PSHRE lead.
5. Identifying need and monitoring impact of interventions | To ensure that 'resilience conversation' discussion sytem is in place across the school and to develop an electronic system for recording interventions across the school. | Data will be used to monitor well-being and improve intervention by better understanding the needs of our students. Evaluation of interventions possible through system. | Named staff member/team | On Going | Photocopying costs. Development time - interventions recording. | SIP | Training for whole staff 13th Nov 2017 |  | Level 1 training was completed for all staff. Awaiting dates of level 2. Meeting to take place in school January with Headstart to confirm Data protection policy is adhered to. | Cordinator to assist Safeguarding lead with data return and both to feedback best practise to other staff using resilience based conversations.
1. Leadership and management that supports and champions efforts to promote emotional health and wellbeing | To include a focus on the development of student resilience and on well-being in school in the School Improvement Plan over the next 5 years. | Provides a focus for well-being and helps in raising whoe school awareness. | Named staff member/team | Yearly | None | SIP | Completed for 2017-18 |  | SIP Completed | Lead.
3. Enabling student voice to influence decisions | To create opportunities for student voice by setting up student working parties. Relevant ideas implemented. | Allows students to take ownership for addressing their own well-being. | Named staff member/team | February 2018 | Staff time to run sessions. Associated project costs. | SIP | Not started. |  | Youth health champions meet weekly. Students have requested a LGBT group is set up which we are looking at. Student voice meet termly with SLT. | Set up a speak out group. Possibly include primary students in YHC campaigns?
2. Curriculum, teaching and learning to promote resilience and support social and emotional learning | To evaluate the school rewards system and ensure that the number of achievement points increases when compared with 2016-17. | Data is shared with staff and students on a weekly basis with a view to improving student self-esteem. Reward points data evaluated. | Named staff member/team | July 2018 | Setting up of new Mintclass system. Preparation of weekly data. Associated costs in terms of rewards. | SIP | Mintclass system in place and data being shared. |  | Termly rewards have been issued and all students have been on reward trip to cinema and some to pantomine. Older students have received a gift card.
8. An ethos and environment that promotes respect and values diversity | To improve displays around school respect to resilience and positive mindset. Links drawn to school and community based interventions. | Constant reminder to staff, students and visitors. Students made aware of opportunities and support available to students across the school. | Named staff member/team | On-going | Display resource costs and staff time. | SIP | Not yet started |  | We are in process of planning the official opening of the Wellbeing centre and displays are being designed to advertise this event. Wellbeing and mindset posters have been displayed in the wellbeing rooms. Students are colouring minfulness posters to go on the wall in the smaller wellbeing room. | Information board for parents in reception.
8. An ethos and environment that promotes respect and values diversity | Safe Space - New My zone space for KS3 located. Students referred following domains based conversations. | Students will feel more supported in school and have access to help with their emotional difficulties and positive wellbeing. Measured by logging number of students who access this provision and through student interviews. | Named staff member/team | September 2017 and on-going | 2 staff - duty payments | SIP | In place |  | KS3 students have been referred to My Zone by college staff to access at lunchtimes. The area has a large space both inside and outside. Students accessing this are monitored and needs accessed. | My Zone data to be shared with Headstart team so we can include in evidence.
5. Identifying need and monitoring impact of interventions | To set up a new wellbeing centre which will provide a range of workshop povisions for domains-referred students. Workshops to be offered:- Bereavement, Anxiety, Day Programme, Emotional Resilience, Be Free, Academic Resilience. | Students will be able to access specific support sessions with experts in the particular fields. Evaluated by workshop evaluations. | Named staff member/team | 2017-12-01 | Staffing of Centre, staffing of workshops, decoration and furniture, development of resources for session delivery. | SIP | Room decorated and online booking system developed. |  | Rooms had been decorated, a new carpet layed and new furniture ordered and in place including a TV for training / workshops. All bookings are made via WBR at the moment so we can monitor use. Emotional resilience workshop is being carried out weekly. Taming my temper from Mind - anger management course has been purchased and will commence in January. The Day programme is due to be run in January. The Be free programme is also booked for the new year. The young carers meet in the room and recently had their Christmas part in there.
5. Identifying need and monitoring impact of interventions | To offer breaktime and lunchtime drop in sessions via the Wellbeing Centre. | Students will build friendships and seek support as required without need for a referral. This will build confidence. Evaluated by number of attendees and evaluation of provision/student interviews. | Named staff member/team | 2018-01-01 | Staffing of Centre during lunchtime and breaktimes. Costs for running workshops. | SIP | Room decorated and staffing sourced. |  | Staff rota in place starting next term. | Space to be advertised and spoken about more.
8. An ethos and environment that promotes respect and values diversity | To train peer mentors (years 7 9, 12). Mentees identified via resilience conversations. | Students will feel better supported and will be able to seek advice from another young person. Impact measured via survey results. | Named staff member/team | November 2017 - May 2018 | None | SIP | First session delivered to year 9. |  | Year 9 students have been trained and are awaiting their mentees. A date has been set to train the year 12 students. | Rolling programme to be planned for next year.
7. Targeted support and appropriate referral | To deliver individual student mentoring sessions via Wellbeing Centre following resilience conversation and inclusion team referrals. | Students will feel better supported and will be able to seek advice from another young person. Impact measured via survey results. | Named staff member/team | 2017-12-01 | Staff mentor cost | SIP | Mentor sourced. |  | Students have been receiving one to one mentoring from our christian worker. AT the moment he is seeing ten students per week. | Review of peer mentoring system to take place.
7. Targeted support and appropriate referral | To adress the needs of school refusers by offering a personlised reintegration programme which will include resilience sessions and return to education plans. | Students will slowly build confidence in returning to the school environment. Return figures analysed. | Named staff member/team | 2018-03-01 | Staff time | Attendance improvement programme | Not yet started. |  | We have a list of students to write a re-integration programme for starting next term. | Two school refusers using space to access work and receive appropriate support with the aim to reengage if possible. Coordinatior working on new proposal to be approved by lead.
7. Targeted support and appropriate referral | To set up a Key Stage 2/3 buddy system around transition. | Students will feel better supported and will be able to seek advice from another young person. Impact measured via transition feedback. | Named staff member/team | 2018-05-01 | Staff time for training buddies. | SIP | Not yet started. |  | We will be training students in the new year who will then go on out to the primary schools to meet their mentees. The FLO team from discovery college will be leading on this. | Peer mentoring training to be completed by end of May 2018. Year 5 students then to be trained by sixth formers.
6. Working with parents/carers | To set up a Wellbeing page on the school website and social media sites so that the community can be kept informed of the progress and support available to students both in school and via the Hub. | Parent, carers, students and staff have wellbeing information to hand at all times if needed. | Named staff member/team | 2018-01-01 | Staff time, Computer equipment and access | SIP | Not started yet |  | A newsletter has been written and will be sent out to parents, staff and students. A wellbeing page is to be set up next term. | Discussions in place for new website page.
4. Staff development to support their own wellbeing and that of students | To have a specific policy on student and staff wellbeing and mental health so a consistent approach is reached by all | Parent, carers, students and staff can see that Wellbeing is embedded in the Hschool's ethos and have a guidance of who to speak to and what support is available. | Named staff member/team | 2017-01-18 | Staff time, policy template | SIP | Not started yet |  | Look at approved template. Decision to be made if we add to ethos for learning policy or have a standalone policy. | Policy written awaiting approval from SLT.
Next year we only have one year group so should be easier but planning needs to be earlier.

## Sheet3
progress | Chapters
Not started | C1.1
In progress | C1.2
On hold | C1.3
No longer needed | C2.1
Complete | C2.2
C2.3
C3.1
C3.2
C3.3